## To Do
Sl No. | Task | Initiation On | Initiated By | Owner | Deadline | Actual Delivery | Progress
1 | Defining Innovation- Quantitatively | 2014-10-08 | Edwin | Manish |  | 2014-10-24 | Under review- Science of Innovation;
2 | Structuring 'Creation of Innovation' | 2014-10-08 |  |  |  | 2014-10-24 | Discussion pending
3 | Structuring 'Outcome of Innovation' | 2014-10-08 |  |  |  | 2014-10-24 | Modified to 5
4 | Identifying Metrics for Innovation Measurement | 2014-10-08 |  |  |  | 2014-10-24 | Modified to 5
5 | Science of Innovation- examples, use cases, metrics | 2014-10-27 | Edwin | Manish
6 | Adobe-Nielson tie up- Innovation offerings | 2014-10-26 | Bala | Manish | 2014-10-29 |  | Initiated
| Learn Architecture Capability Maturity Model (ACMM) |  | Edwin/Manish
| Statistical Validation of ACMM |  | Manish
| Blue Ocean Strategy (BOS)- Learn | 2014-10-15
Evangelizing Material for BOS
BOS & Innovation- tying up
H2 team tasks
| ACE beta testing in 4 accounts- Apple, ASML, McK, NetApp | [5 empty] | NetApp- Expectation Map initiated; Propositions for others being prepared
Branding- Ideastorm/IMG ?
| Account connect- Bangalore |  |  | Manish
AIM- Intel, Infineon
| Newsletter | [5 empty] | Articles being sourced, editorials by Maitreyi
| Tata Innovista support | [5 empty] | Promotion and Participation from HiTech
Brochure/flyer for IMG, ACE, AIM

## Work Clock
Date | Work | Details | Meetings | Details2 | L&D- courses | Details3 | L&D- Study & others | Details4 | Personal errands & breaks | Details5 | Misc/ Untracked | Details6 | Clock
2014-09-17 | 2 | Stage gate | 1 |  | 1 | Environ setup | 0 |  | 3 | ICICI Mutual fundsetc. | 3 |  | 10
2014-09-18 | 1 | Miscellany | 0 |  | 1 | PM WBT n environ setup | 0 |  | 4 | ICICI c/c applied | 2 |  | 8
2014-09-19 | 2.5 | Idea Management | 1.5 | Account BP Review | 0 |  | 0 |  | 3 |  | 1 |  | 8
2014-09-22 | 1.5 | Idea Management | 2.5 | AIM 2.0- Apple deployment | 1 | Webinars setup (failed) | 0 |  | 2.75 | Sleep & lunch | 1.5 |  | 9.25
2014-09-23 | 1 | CTO snapshot | 2.5 | AIM 2.0- Apple, HP | 4.5 | PM WBT 1/28 | 0 |  | 1.25 | Lunch & breaks | 1 |  | 10.25
2014-09-24 | 2 | Idea Management; AIM 2.0 | 3 | Idea Management Process; AIM 2.0 deployment | 0 |  | 2.5 | News, tech trends | 1 | Lunch & breaks | 0 |  | 8.5
2014-09-25 |  |  |  |  | 3.5 | Webinars- Azure, Scalable Content Marketing | 1 | Flat UI- metro, iOS 6-7,Android L | 1.5 |  | 0 |  | 6
2014-09-26 | [8 empty] | 1.5 | Lunch & breaks | 0 |  | 1.5
2014-09-29 | [8 empty] | 1.5 | Lunch & breaks | 0 |  | 1.5
2014-09-30 |  |  | 2 | Debate & Discussions |  |  |  |  | 1.5 | Lunch & breaks | 0 |  | 3.5
2014-10-01 | 4 | Account analysis & overview | 2.5 | Identifying and analyzing target accounts | 0 |  | 1.5 | News, mail etc. | 1.5 | Lunch & breaks | 0 |  | 9.5
2014-10-06 | 3.5 | Target account study- ASML, NXP, Infographic for Ideastorm | 0 |  | 0 |  | 4 | News, mail, Knome blog, study | 1 | Lunch & breaks | 0 |  | 8.5
2014-07-10 | 1 | IBM Watson analytics study | 3 | Conflict resolution | 1 | Spanish revision | 2.5 | News, Knome, LinkedIn articles | 1 | Lunch & breaks | 0 |  | 8.5
2014-10-08 | 2.5 | Revision of Innovation Trends Framework- Figures | 1.5 | TEG Induction-2 | 2 | Excel shortcuts, Productivity tools; Competency list | 2.5 | Knome, Impact sourcing study | 1 | Lunch | 0 |  | 9.5
2014-10-09 | 3 | Math of Innovation- first draft | 0.5 | Routine discussions | 2 | PM WBT 2/28; Excel shortcuts | 3 | News, Knome, LinkedIn articles | 1 | Lunch & breaks | 0 |  | 9.5
2014-10-10 | 4 | Math of Innovation- revision; science Paper search & study | 2 | Team meeting, work discussions | 1.5 | PM WBT 2/28 | 0.5 | News, Knome, LinkedIn articles | 1 | Lunch & breaks | 0 |  | 9
2014-10-13 | 2.5 | Gartner Trends Analysis; Design Thinking thesis structure review | 1.5 | EBS random media tools session- useless | 1.5 | Appraisal process clarification; Role tagging follow up | 1 | Mail, news | 1.5 | Catching up with friends over lunch | 0 |  | 8
2014-10-14 | 4 | Gartner Trends Analysis- relevance report for IMG | 2 | IASA- ACMM seminar by Edwin | 1.5 | Skill level update & overview of competencies gap | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Communicating with Humana (Healthcare) for Murali | 0 |  | 10.5
2014-10-15 | 3.5 | Blue Ocean Strategy- study HBR paper; Math of Innovation- study | 0 |  | 1 | Study- HBR papers | 1.5 | Mail, news, LinkedIn, Knome | 2 | Lunch & breaks | 0 |  | 8
2014-10-16 |  |  | 0 | [7 empty] | 0 |  | 0
2014-10-17 | 4 | Math of Innovation- revision; science Paper search & study | 0.5 | Chat with Richa- work and life | 0 |  | 1 | Mail, news, Knome, LinkedIn | 2 | Errands & Breaks | 0 |  | 7.5
2014-10-20 | 5.5 | Math of Innovation- Oslo Manual, Harvard innovation | 1.5 | Team meeting; conference discussion with Bala | 0 |  | 1 | Mail, news, Knome, LinkedIn | 1 | Lunch & breaks | 0 |  | 9
2014-10-21 | 4 | Oslo Manual, acad innovation research | 2 | Networking @ Dhara | 0 |  | 1.5 | Networking groundwork | 0.5 | Lunch | 0 |  | 8
2014-10-23 | 4.5 | Math of Innovation- final draft | 0 |  | 0 |  | 2.5 | Mail, news, LinkedIn, Knome | 1.5 | Home Lunch |  |  | 8.5
2014-10-24 | 1.5 | iCALMS role goal planning | 0 |  | 3 | Webinar: Effective Strat Planning; Duolingo Spanish revision | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Lunch & breaks | 1 |  | 8.5
2014-10-27 | 4.5 | IMG logo rework; Nielson-Adobe alliance study | 2.5 | Discussions with Richa, Edwin, Bala; TEG trends discussion meeting | 0 |  | 1 | Mail, news, LinkedIn, Knome | 0.75 | Lunch & breaks |  |  | 8.75
2014-10-28 | 2 |  | 2 | Goals discussion for HY-II | 0 |  | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Lunch & breaks |  |  | 7
2014-10-29 | 1.5 | InnoVista 2015 | 2.5 | TEG Bid win/loss discussion; IMG discussion for Innovista | 1 | Webinar registrations Innovation series from Stanford | 1.5 | Mail, news, LinkedIn, Knome | 2 | Errands & Breaks |  |  | 8.5
2014-10-30 | 5 | InnoVista 2015; Goal Plan for HY | 2 | KSS- IoT in Healthcare; Team conversations | 0 |  | 1 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 9
2014-10-31 | 2 | InnoVista 2015 Inputs and Pitch | 3 | BizDevOps-CTO talk; Weekly Team meet | 1 | Library study- HBR; Steve Jobs Innovation | 1.5 | Mail, news, LinkedIn, Knome | 1 | Errands & Breaks |  |  | 8.5
2014-11-03 | 2 | Goal Action Plan for HY II | 2 | Goals discussion for HY-II- with Edwin | 0 |  | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Lunch & breaks | 1 |  | 8
2014-11-04 | 2 | Goal Action Plan for HY II | 1 | Template Discussion with Richa | 1 | BCG perspectives on Business Model Innovation | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Lunch & breaks |  |  | 7
2014-11-05 | 4 | Idea analysis; WSR reporting; Course study on R-programming | 1.5 | Idea discussion- Utility Computing Management software | 2 | Stanford webinars: Design Thinking & Creativity, Art of Critique: I like/ I wish | 2 | Mail, news, LinkedIn, Knome | 1.5 | Errands & Breaks |  |  | 11
2014-11-06 | 4.5 | Setup of R-environ; Science of Innovation; TCS Asset locating and study | 2.5 | WSR Discussion; Qlik Sense Technical Review | 1.5 | Online Course- R; | 1 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 10.5
2014-11-07 | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-11-10 | 2.5 | Science of Innovation- revision & data gathering | 1 | TEG CoE Knowmax pages review call | 3.5 | Cloud integration: strategic approach- Tech Asset Review | 1 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 9
2014-11-11 | 3.5 | Science of Innovation- study & data gathering | 1 | InnoVista Sensitization CTO call | 1.5 | Online Course- R; | 1.5 | Mail, Blog on LinkedIn, Knome | 1 | Lunch & breaks |  |  | 8.5
2014-11-12 | 3 | Science of Innovation- data structuring; weekly transactional stuff | 1.75 | InnoVista Sensitization TEG call; Stanford Webinar | 0 |  | 2 | Mail, news, LinkedIn, Knome | 1.5 | Errands & Breaks |  |  | 8.25
2014-11-13 | 4 | Science of Innovation- data gathering; Innovation study; Adobe-Nielsen alliance study | 0.5 | Internal team calls, chat, discussions | 1 |  | 1.5 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 8
2014-11-14 | 1 | Adobe-Nielsen alliance study and analysis | 4 | Adobe-Nielsen offering discussion; Team weekly meeting; PwC- analytics for service desk improvement- first discussion | 1.5 | Cloud Computing- adoption strategy- Tech Asset Review | 1.5 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 9
2014-11-17 | 2 | Random miscellaneous work | 1 | Richa, Maitreyi | 2 | Misc study | 2 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 8
2014-11-18 | 2 | InnoVista and misc | 1 | Richa, Edwin, Maitreyi | 2 | Misc study | 1.5 | Mail, news, LinkedIn, Knome | 1.5 | Lunch & breaks |  |  | 8
2014-11-19 | 3 | Study for Dr. Dobbs conference; sanitize Bala's ppt | 1.5 | Chats & discussions with Edwin, Maitreyi & Richa | 1 | Spanish revision | 1.5 | Mail, news, LinkedIn, Knome | 2 | Errands & breaks |  |  | 9
2014-11-20 | 6 | Dr.Dobb's conference | 2 | Meeting with Bala, conference networking | 0 |  | 1.5 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks | 2.5 | Commute | 13
2014-11-21 | 5.5 | Dr. Dobb's conference | 2 | Conference networking | 0 |  | 1 | Mail, news, LinkedIn, Knome | 0.5 | Lunch & breaks | 1.5 | Commute | 10.5
2014-11-24 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-11-25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-11-26 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-11-27 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-11-28 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-12-01 | 3.5 | Model update; Idea follow on; Ideas hunt | 3 | TEG all hands meeting; Xamarin introduction | 0 |  | 1 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 8.5
2014-12-02 | 4 | Big Data CoE white papers; data acquisition | 1 | Plan and discussions | 1 | MOOC- Innovation | 1 | Mail, news, LinkedIn, Knome | 1.5 | Breaks and sickness recovery |  |  | 8.5
2014-12-03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-12-04 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
2014-12-05 | [12 empty] | 0
2014-12-08 | 1.5 | Blog posts, Knome updates | 1 | Mentorship request | 1.5 | MOOC- Innovation |  |  | 1 | Lunch & breaks |  |  | 5
2014-12-09 | 4.5 | White paper rework; Dr. Dobb's ppt outline | 1.5 | Discussion & scheduling | 1 | MOOC- Innovation | 1 | Mail, news, LinkedIn, Knome | 1 | Lunch & breaks |  |  | 9
2014-12-10 | [12 empty] | 0
2014-12-11 | [12 empty] | 0
2014-12-12 | 2 | Design Thinking, Tech Heat map, misc clearing | 2 | Discussions | 1 | MOOC- Innovation | 1 | Mail, news, LinkedIn, Knome | 2 | Lunch & breaks |  |  | 8
2014-12-15 | [12 empty] | 0
2014-12-16 | [12 empty] | 0
0
0
0
0
0